## Slide 1: Lecture 7-8
MANAGING AND TRACKING THE SOFTWARE PROJECT

## Slide 5: Questions from a Customer
Do you understand my problem and needs?
Can you design a system to solve my problems or satisfy my needs?
How long will it take to develop the system?
How much will it cost to develop the system?

## Slide 6: Project Schedule
Describes the software-development cycle for a particular project by
  enumerating the phases or stages of the project
  breaking each phase into discrete tasks or activities to be completed
Portrays the interactions among the activities and estimates the times that each task or activity will take

## Slide 7: Project Schedule (Contd.)
Understanding customer’s needs by listing all project deliverables
  Documents
  Demonstrations of function
  Demonstrations of subsystems
  Demonstrations of accuracy
  Demonstrations of reliability, performance or security
Determining milestones and activities to produce the deliverables

## Slide 8: Project Schedule (Contd.)
Activity: takes place over a period of time
Milestone: completion of an activity -- a particular point in time
Precursor: event or set of events that must occur in order for an activity to start
Duration: length of time needed to complete an activity
Due date: date by which an activity must be completed

## Slide 9: Project Schedule (Contd.)
Project development can be separated into a succession of phases which are composed of steps, which are composed of activities (Work Breakdown Structure)

## Slide 10: Project Schedule (Contd.)
Table 3.1 shows the phases, steps and activities to build a house
  landscaping phase
  building the house phase
Table 3.2 lists milestones for building the house phase

## Slide 11: Work Breakdown Structure (WBS) Phases, Steps, and Activities in Building a House

## Slide 12: Milestones

## Slide 13: WBS and Activity Graphs
Work breakdown structure depicts the project as a set of discrete pieces of work
Activity graphs depict the dependencies among activities
  Nodes: project milestones
  Lines: activities involved

## Slide 14
Activity graph for building a house
Does it tell us:
About completion of the project?
Duration of the project?
How can we modify the graph to estimate completion?
Mention duration of each activity?
Identify precursor events
2.7, 2.8, 3.4, 3.6?
1.1 and 1.2 are precursor to Excavation activity

## Slide 16: Estimating Completion
Adding estimated time in activity graph of each activity to be completed tells us more about the project's schedule

## Slide 17: Estimating Completion Critical Path Method
Minimum amount of time required to complete a project
  Reveals those activities that are most critical to completing the project on time
Real time (actual time): estimated amount of time required for the activity to be completed
Available time: amount of time available in the schedule for the activity's completion
Slack time: the difference between the available time and the real time for that activity

## Slide 18: Estimating Completion Critical Path Method
Critical path: the slack at every line is zero
  can be more than one in a project schedule
Slack time =
  available time – real time
  latest start time – earliest start time
Paths????
Longest Path???

## Slide 20: Estimating Completion Critical Path Method

## Slide 22
Example: to track progress of building a communication software
What is it?

## Slide 23: Tracking Progress Gantt Chart
Activities shown in parallel
  helps understand which activities can be performed concurrently

## Slide 24: Tracking Resource Allocation Resource Histogram

## Slide 29: 3.2 Project Personnel
Key activities requiring personnel
  requirements analysis
  system design
  program design
  program implementation
  testing
  training
  maintenance
  quality assurance
Assignment of staff depends on
  project size
  staff expertise
  staff experience
Different responsibilities for different people

## Slide 30: 3.2 Project Personnel Choosing Personnel
Decide roles of project team members
Decide which kind of people do we need for each role
Select appropriate personnel for each role

## Slide 31: 3.2 Project Personnel Choosing Personnel
How do two people differ from each other:
  Ability to perform work
  Interest in work
  Experience with
    similar applications
    similar tools, languages, or techniques
    similar development environments
  Training
  Ability to communicate with others
  Ability to share responsibility
  Management skills

## Slide 32: 3.2 Project Personnel Communication
A project's progress is affected by
  degree of communication
  ability of individuals to communicate their ideas
Software failures can result from breakdown in communication and understanding

## Slide 33: 3.2 Project Personnel Communication (continued)
Line of communication can grow quickly
If there is n worker in project, then there are n(n-1)/2 pairs of communication

## Slide 34: 3.2 Project Personnel Sidebar 3.1 Make Meeting Enhance Project Progress
Common complains about meeting
  the purpose is unclear
  the attendees are unprepared
  essential people are late or absent
  the conversation veers away from its purpose
  participants do not discuss, instead argue
  decisions are never enacted afterward
Ways to ensure a productive meeting
  clearly decide who should be in the meeting
  develop an agenda
  have someone who tracks the discussion
  have someone who ensures follow-up actions

## Slide 35: 3.2 Project Personnel Work Styles
Extroverts: tell their thoughts
Introverts: ask for suggestions
Intuitives: base decisions on feelings
Rationals: base decisions on facts, options

## Slide 36: 3.2 Project Personnel Work Styles (continued)
Horizontal axis: communication styles
Vertical axis: decision styles

## Slide 40: 3.2 Project Personnel Work Styles (continued)
Work styles determine communication styles
Understanding workstyles
  help to be flexible
  give information based on other's priorities
Impacts interaction among customers, developers and users

## Slide 48: 3.2 Project Personnel Project Organization
Depends on
  backgrounds and work styles of team members
  number of people on team
  management styles of customers and developers
Examples:
  Chief programmer team: one person totally responsible for a system's design and development
  Egoless approach: hold everyone equally responsible

## Slide 49: 3.2 Project Personnel Project Organization: Chief Programmer Team
Each team member must communicate often with chief, but not necessarily with other team members

## Slide 50: 3.2 Project Personnel Project Organization (continued)
Characteristics of projects and the suggested organizational structure to address them

## Slide 51: 3.2 Project Personnel Sidebar 3.2 Structure vs. Creativity
Experiment by Sally Phillip examining two groups building a hotel
  structured team: clearly defined responsibilities
  unstructured team: no directions
The results are always the same
  Structured teams finish a functional Days Inn
  Unstructured teams build a creative, multistoried Taj Mahal and never complete
Good project management means finding a balance between structure and creativity

## Slide 52: References
Pfleeger Book slides from UCF
Disclaimer!
A few slides have been reused from UCF slides for the SE course

## Slide 53: Exercise
Recipe of making Chicken Biryani is given below:
In a large deep cooking pot, pour 2 tablespoons vegetable oil (or ghee) fry potatoes until brown, drain and reserve the potatoes. Add remaining 2 tablespoons oil to the pot and fry onion, garlic and ginger until onion is soft and golden. Add chili, pepper, turmeric, cumin, salt and the tomatoes. Fry, stirring constantly for 5 minutes. Add yogurt, mint, cardamom and cinnamon stick. Cover and cook over low heat, stirring occasionally until the tomatoes are cooked to a pulp. It may be necessary to add a little hot water if the mixture becomes too dry and starts to stick to the pan.
When the mixture is thick and smooth, add the chicken pieces and stir well to coat them with the spice mixture. Cover and cook over very low heat until the chicken is tender, approximately 35 to 45 minutes. There should only be a little very thick gravy left when chicken is finished cooking.
Soak the rice in warm water, then wash in cold until the water runs clear. Heat appropriate quantity of water in a separate large deep cooking pot. Add the washed rice in slightly hot water. Keep the heat on until the water boils. When most of the water dries out and the rice have been boiled (but there remain some water in the pot), the rice are ready to be mixed with the chicken gravy.
Mix the chicken gravy and the boiled rice layer by layer in a deep pot. When both have been put in the same pot, mix them gently. Cover the pot tightly, turn heat to very low and steam for 20 minutes. Do not lift lid or stir while cooking. After 20 minutes, biryani is ready to serve
Note: We have many cooking pans and many stoves available at the start of the project.
To Do:
Identify phases, steps, activities, and milestones of this project. After this identification provide the work breakdown structure. Also draw activity graph of the project. State your assumptions clearly.

## Slide 54
Quiz on MCQs

## Slide 55: Using scientific knowledge to design solution of a new problem is called
Scientific method
Engineering method
Commercial production method
Craft
All

## Slide 56: The waterfall model is more suitable for ________
Scientific method
Engineering method
Commercial production method
Craft
All

## Slide 57: The waterfall model with prototyping is more suitable for ________
Scientific method
Engineering method
Commercial production method
Craft
All

## Slide 58: Method + tool =

## Slide 59: Fault leads to _____

## Slide 60: A software should not crash, this quality is called ______

## Slide 61: A software should use minimum resources i.e. time and memory, this quality is called ______

## Slide 62: A software should be able to run on all platforms, this quality is called ______

## Slide 63: If the developer says , “you are not supposed to use it this way!” it means, the software lacks______

## Slide 64: If the customers says , “It is not what I meant!” it means, the software lacks_ _____

## Slide 65: We are going to build a project where fingers are crossed about our success.. What model should we use?

## Slide 66: We are going to build a project where customer is not willing to pay until we deliver.. What model should we use?

## Slide 67: We are going to build a project where we need customers live feedback and the project can be finished in 15 days…. What is best approach